## Read me
Design-Build-Fly inventory (DBF-INV-001)
Owner: Tristan Hottier, Inventory Czar. Lift + cruise VTOL, design revision 0.3.1.
How to use
Inventory tab: one row per stock line. P- rows are bought, M- rows are made in-house, N- rows are the proposed Nautical Wings carbon props.
Edit only the blue cells: Qty ordered, Qty on hand, Status, Location, Order date, Received date, Inspected, Actual USD, Notes.
Black cells are formulas (Ext USD, Qty still to get). Status and Inspected use dropdowns; status colours update by themselves.
When a delivery arrives: count it against the packing slip, set Qty on hand, Received date and Inspected, label the item with its ID and put it in its kit bin (K1 to K7).
Budget tab: totals against the $2,000 cap, the crash reserve, spend by kit and the effect of the Nautical Wings prop swap.
Where the numbers come from
Rows were generated on 2026-10-19 from docs/purchasing/C0_BOM.csv (prices checked 2026-10-13) and the CAD assembly in cad/params.txt, by inventory/build_inventory.mjs in the DBF-VTOL repo.
Nothing has been ordered or built yet, so every on-hand quantity starts at 0. Re-check prices before ordering.
Overview page: Inventory-Overview.html in the DBF-VTOL repo.

## Budget
Budget against the $2,000 cap
Blue cells are inputs; black cells are formulas over the Inventory tab.
Inputs
Hardware budget cap | 2000 | Source: docs/DESIGN-BASIS.md R6 (fixed, includes tax and shipping)
Sales/use tax rate (Berkeley) | 10.25% | Source: C0_BOM.csv, CDTFA rate 2026-10-01
Shipping allowance (estimate) | 100 | Source: C0_BOM.csv; estimate, price at checkout
Plan (BOM prices)
Goods subtotal (Buy lines)
Sales/use tax
Shipping allowance
Committed spend
Crash reserve left under the cap
Reserve check: BOM says $102.08
Actual spend (fill Actual USD on the Inventory tab, tax and shipping included)
Spent so far
Left under the cap
Nautical Wings carbon props (proposed, free)
Retail prop lines on hold (goods)
Same with tax
Reserve if the NWA props are confirmed (EST) |  | EST: assumes the props are free with no shipping or import cost; shipping allowance unchanged
By kit
Kit | Name | Lines | Still to get (lines) | Plan goods (USD)
Total
Note on B4: Source: docs/DESIGN-BASIS.md R6 (fixed, includes tax and shipping)
Note on B5: Source: C0_BOM.csv, CDTFA rate 2026-10-01
Note on B6: Source: C0_BOM.csv; estimate, price at checkout

## Inventory
ID | Item | Type | Category | Kit | CAD part | Qty needed | Qty ordered | Qty on hand | Qty still to get | Status | Vendor | Unit USD | Ext USD | Actual USD | Made from | Process | Location | Order date | Received date | Inspected | Source | Notes
P-01 | Polymaker PA6-CF20 500 g (motor mounts: HDT 173 °C) | Buy | Airframe | K7 |  | 1 | 0 | 0 |  | To order | — | 39.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: AM §2d | PETG too close to motor heat (sec. 12)
P-02 | Hot-wire bow, nichrome + bench supply (wing cores) | Buy | Airframe | K7 |  | 1 | 0 | 0 |  | To order | — | 40 |  |  |  |  | — |  |  |  | C0_BOM.csv: EST allowance | not priced; borrow if a makerspace has one
P-03 | Scotch heavy-duty packing tape, 6 rolls (skin) | Buy | Airframe | K7 |  | 1 | 0 | 0 |  | To order | Amazon | 19.98 |  |  |  |  | — |  |  |  | C0_BOM.csv: BF §2 amazon.com
P-04 | Hardware kit: XT90S, wire, extensions, screws, inserts, horns, pushrods, hinge tape, heat shrink, UBEC, epoxy | Buy | Airframe | K7 |  | 1 | 0 | 0 |  | To order | Amazon | 124.01 |  |  |  |  | — |  |  |  | C0_BOM.csv: BF §3 amazon.com (itemised in file)
P-05 | ELEGOO PETG 1 kg (clamps, pod frames, gear clamps) | Buy | Airframe | K7 |  | 2 | 0 | 0 |  | To order | Amazon | 12.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BF §5
P-06 | BNTECHGO 12 AWG silicone wire, 2nd pack (ESC feeds) | Buy | Airframe | K7 |  | 1 | 0 | 0 |  | To order | Amazon | 14.98 |  |  |  |  | — |  |  |  | C0_BOM.csv: BF §3a item 3 amazon.com
P-07 | 14 AWG silicone wire (pusher / BEC feeds) | Buy | Airframe | K7 |  | 1 | 0 | 0 |  | To order | Amazon | 9.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BF §3b amazon.com
P-08 | XT60H connectors 12 pairs (boom harness disconnects) | Buy | Airframe | K7 |  | 1 | 0 | 0 |  | To order | Amazon | 6.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BF §3b amazon.com
P-09 | 300 mm servo extension leads, 2nd pack | Buy | Airframe | K7 |  | 1 | 0 | 0 |  | To order | Amazon | 6.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BF §3a item 4 amazon.com
P-10 | Foam-safe glue 4 oz | Buy | Airframe | K7 |  | 1 | 0 | 0 |  | To order | Amazon | 12.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BF §3b amazon.com
P-11 | ShareGoo LiPo battery straps (10) | Buy | Airframe | K7 |  | 1 | 0 | 0 |  | To order | Amazon | 7.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BF §3b amazon.com
P-12 | Ovonic 6S 6500 100C — 2-pack listing (2 packs) | Buy | Energy | K4 | Battery_6S_LiPo | 1 | 0 | 0 |  | To order | Amazon | 138.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BE §1 amazon.com | second pack per R7; EC5 leads: re-terminate to XT90S
P-13 | HTRC C150 charger (150 W, ~6 A on 6S) | Buy | Energy | K6 |  | 1 | 0 | 0 |  | To order | Amazon | 56.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BE §2 amazon.com/dp/B0H4QLJYHY
P-14 | JeeFly 1755 carbon prop (pair) | Buy | Lift propulsion | K2 | Lift_Prop | 2 | 0 | 0 |  | Hold: NWA swap pending | Amazon | 18.6 |  |  |  |  | — |  |  |  | C0_BOM.csv: BL props amazon.com/dp/B0FJ21V736 | $4.99 delivery, likely CN; Retail fallback if the Nautical Wings carbon props are not confirmed
P-15 | SoloGood 45A ESC (4-pack) | Buy | Lift propulsion | K2 |  | 2 | 0 | 0 |  | To order | Amazon | 39.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BL ESCs amazon.com | 4 lift + pusher + 3 spare; low stock: fallback LANRC 35A
P-16 | JeeFly 1755 spare pair (amazon.com) | Buy | Spares | K2 |  | 1 | 0 | 0 |  | Hold: NWA swap pending | Amazon | 18.6 |  |  |  |  | — |  |  |  | C0_BOM.csv: BL | Retail fallback if the Nautical Wings carbon props are not confirmed
P-17 | Du-Bro 230 pushrod 5-pack (spares) | Buy | Spares | K7 |  | 1 | 0 | 0 |  | To order | Amazon | 12.48 |  |  |  |  | — |  |  |  | C0_BOM.csv: BF §3b amazon.com
P-18 | Tenergy LiPo bag | Buy | Test & safety | K6 |  | 1 | 0 | 0 |  | To order | Amazon | 8.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BE §3
P-19 | Watt meter 150 A / 60 V | Buy | Test & safety | K6 |  | 1 | 0 | 0 |  | To order | Amazon | 12.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BE §3
P-20 | IR thermometer | Buy | Test & safety | K6 |  | 1 | 0 | 0 |  | To order | Amazon | 8.98 |  |  |  |  | — |  |  |  | C0_BOM.csv: BE §3
P-21 | 20 kg load cell + HX711 kit (thrust stand) | Buy | Test & safety | K6 |  | 1 | 0 | 0 |  | To order | Amazon | 8.98 |  |  |  |  | — |  |  |  | C0_BOM.csv: BE §4
P-22 | Arduino Nano clone (thrust stand) | Buy | Test & safety | K6 |  | 1 | 0 | 0 |  | To order | Amazon | 8.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BE §4
P-23 | APC 14x8.5EP pusher prop | Buy | Cruise propulsion | K4 | Pusher_Prop_14in | 3 | 0 | 0 |  | Hold: NWA swap pending | APC Propellers | 6.79 |  |  |  |  | — |  |  |  | C0_BOM.csv: PB 1c | Retail fallback if the Nautical Wings carbon props are not confirmed
P-24 | EMAX ES3005HV servo | Buy | Controls | K1 |  | 5 | 0 | 0 |  | To order | EMAX USA | 19.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BA §6 shop.emax-usa.com | 2 ailerons, elevator, 2 rudders
P-25 | EMAX ES3005HV spare servo | Buy | Spares | K1 |  | 1 | 0 | 0 |  | To order | EMAX USA | 19.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BA §6
P-26 | Harbor Freight 0.50 cal ammo can (pack storage) | Buy | Test & safety | K6 |  | 1 | 0 | 0 |  | To order | Harbor Freight | 19.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BE §3
P-27 | Holybro MS5525DSO + PT40 airspeed | Buy | Avionics | K4 | Pitot_Tube | 1 | 0 | 0 |  | To order | Holybro (ships CN) | 59.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BA §3 holybro.com | ships CN
P-28 | FOAMULAR NGX F-250 2 in x 4 x 8 ft (wing cores) | Buy | Airframe | K7 |  | 1 | 0 | 0 |  | To order | Home Depot | 59.97 |  |  |  |  | — |  |  |  | C0_BOM.csv: BF §2 homedepot.com
P-29 | FOAMULAR 150 1 in x 4 x 8 ft (tail, pod) | Buy | Airframe | K7 |  | 1 | 0 | 0 |  | To order | Home Depot | 30.97 |  |  |  |  | — |  |  |  | C0_BOM.csv: BF §2 homedepot.com
P-30 | 6061-T6 tube 1.000 x 0.035 in x 72 in (booms) | Buy | Airframe | K7 |  | 2 | 0 | 0 |  | To order | OnlineMetals | 26.2 |  |  |  |  | — |  |  |  | C0_BOM.csv: BF §1 onlinemetals.com | cut list 0.955 + 0.516 + 0.955 + 0.516 m
P-31 | 6061-T6 tube 1.000 x 0.058 in x 96 in (spar sockets + gear legs) | Buy | Airframe | K7 |  | 1 | 0 | 0 |  | To order | OnlineMetals | 53.97 |  |  |  |  | — |  |  |  | C0_BOM.csv: BF §1 | 2 x 0.8 m sockets + 4 x 0.205 m legs + kerf
P-32 | 6061-T6 tube 0.875 x 0.058 in x 36 in (joiner) | Buy | Airframe | K7 |  | 1 | 0 | 0 |  | To order | OnlineMetals | 18.45 |  |  |  |  | — |  |  |  | C0_BOM.csv: BF §1 | 0.76 m joiner, 0.30 m engagement per side; 0.23 mm clearance
P-33 | HGLRC M100-5883 GPS + compass | Buy | Avionics | K4 |  | 1 | 0 | 0 |  | To order | RaceDayQuads | 20.49 |  |  |  |  | — |  |  |  | C0_BOM.csv: BA §2 racedayquads.com
P-34 | NewBeeDrone BeeID v1.1 Remote ID (FAA DoC RID000001995) | Buy | Avionics | K4 |  | 1 | 0 | 0 |  | To order | RaceDayQuads | 36.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BA §4 racedayquads.com
P-35 | RadioMaster Pocket Crush ELRS | Buy | Avionics | K6 |  | 1 | 0 | 0 |  | To order | RadioMaster | 64.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BA §5 radiomasterrc.com
P-36 | RadioMaster RP3 V2 ELRS receiver | Buy | Avionics | K4 |  | 1 | 0 | 0 |  | To order | RadioMaster | 19.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BA §5
P-37 | CoreWing F405 Wing APP V2 (12 out, 90 A sensor) | Buy | Avionics | K4 |  | 1 | 0 | 0 |  | To order | ReadyMadeRC | 67.26 |  |  |  |  | — |  |  |  | C0_BOM.csv: BA §2 readymaderc.com | ArduPilot target beta-only (4.7.2-beta); fallback Matek F405-WMO $69.99
P-38 | SunnySky X4110S 400KV (pusher) | Buy | Cruise propulsion | K4 | Pusher_Motor | 1 | 0 | 0 |  | To order | SunnySky USA | 46.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BL A3 | same motor as lift: one spare covers both
P-39 | SunnySky X4110S 400KV | Buy | Lift propulsion | K2 | Lift_Motor | 4 | 0 | 0 |  | To order | SunnySky USA | 46.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BL A3 sunnyskyusa.com
P-40 | X4110S spare motor (lift or pusher) | Buy | Spares | K4 |  | 1 | 0 | 0 |  | To order | SunnySky USA | 46.99 |  |  |  |  | — |  |  |  | C0_BOM.csv: BL
M-01 | Left wing panel, NACA 2415 (EST), XPS core + tape skin, chord 239 mm | Make | Fabricated part | K1 | Wing_Panel_L | 1 |  | 0 |  | To make | In-house | 0 |  |  | P-28 | Hot-wire XPS core, packing-tape skin | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-02 | Right wing panel, NACA 2415 (EST), XPS core + tape skin, chord 239 mm | Make | Fabricated part | K1 | Wing_Panel_R | 1 |  | 0 |  | To make | In-house | 0 |  |  | P-28 | Hot-wire XPS core, packing-tape skin | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-03 | Left aileron, 26 % chord, 55 % of panel span | Make | Fabricated part | K1 | Aileron_L | 1 |  | 0 |  | To make | In-house | 0 |  |  | P-28 | Cut from wing panel trailing edge, tape hinge | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-04 | Right aileron, 26 % chord, 55 % of panel span | Make | Fabricated part | K1 | Aileron_R | 1 |  | 0 |  | To make | In-house | 0 |  |  | P-28 | Cut from wing panel trailing edge, tape hinge | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-05 | Wing centre-section saddle over the joiner: XPS block from the budgeted FOAMULAR sheet, taped, with printed PETG root plates (EST) | Make | Fabricated part | K1 | Wing_Saddle | 1 |  | 0 |  | To make | In-house | 0 |  |  | P-28 | XPS block, taped; printed PETG root plates; bore for joiner | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-06 | 6061-T6 1.000 x 0.058 in spar socket, 0.8 m | Make | Fabricated part | K1 | Spar_Tube | 2 |  | 0 |  | To make | In-house | 0 |  |  | P-31 | Cut 0.8 m from 96 in tube | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-07 | 6061-T6 0.875 x 0.058 in joiner, 0.76 m | Make | Fabricated part | K1 | Wing_Joiner | 1 |  | 0 |  | To make | In-house | 0 |  |  | P-32 | Cut 0.76 m from 36 in tube | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-08 | M5 x 30 stainless button screw into a captive nut in the saddle (hardware kit, budget-airframe.md §3a item 5) | Make | Fabricated part | K1 | Wing_Bolt | 2 |  | 0 |  | To make | In-house | 0 |  |  | P-04 | M5 x 30 from hardware kit, captive nut in saddle | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-09 | Front boom, 6061-T6 1.000 x 0.035 in | Make | Fabricated part | K2 | Boom_Front | 2 |  | 0 |  | To make | In-house | 0 |  |  | P-30 | Cut 0.955 m from 72 in tube | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-10 | Rear boom stub carrying the tail, 6061-T6 | Make | Fabricated part | K2 | Boom_Rear_Stub | 2 |  | 0 |  | To make | In-house | 0 |  |  | P-30 | Cut 0.516 m from 72 in tube | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-11 | Printed PETG boom-to-wing clamp at the spar; top meets the wing lower surface | Make | Fabricated part | K2 | Boom_Clamp_Front | 2 |  | 0 |  | To make | In-house | 0 |  |  | P-05 | 3D print, PETG | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-12 | Printed PETG boom-to-wing clamp at 80 % chord; top meets the wing lower surface | Make | Fabricated part | K2 | Boom_Clamp_Rear | 2 |  | 0 |  | To make | In-house | 0 |  |  | P-05 | 3D print, PETG | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-13 | Printed PA6-CF motor mount on boom, covers the boom splice at the rear station (EST) | Make | Fabricated part | K2 | Motor_Mount | 4 |  | 0 |  | To make | In-house | 0 |  |  | P-01 | 3D print, PA6-CF (motor heat) | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-14 | Horizontal stabiliser, NACA 0009 (EST), area from V_h = 0.35 | Make | Fabricated part | K3 | H_Tail | 1 |  | 0 |  | To make | In-house | 0 |  |  | P-29 | Hot-wire or sand XPS, tape skin | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-15 | Elevator, 30 % chord, NACA 0009 | Make | Fabricated part | K3 | Elevator | 1 |  | 0 |  | To make | In-house | 0 |  |  | P-29 | Cut XPS, tape hinge | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-16 | Vertical fin, NACA 0009, lofted taper 65 % tip chord | Make | Fabricated part | K3 | Fin | 2 |  | 0 |  | To make | In-house | 0 |  |  | P-29 | Cut XPS, tape skin | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-17 | Fuselage pod, 0.85 m x 0.16 m, foam + PETG frames + tape (EST) | Make | Fabricated part | K4 | Fuselage_Pod | 1 |  | 0 |  | To make | In-house | 0 |  |  | P-29 | XPS shell on printed PETG frames, taped | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-18 | Avionics hatch blister (EST) | Make | Fabricated part | K4 | Canopy | 1 |  | 0 |  | To make | In-house | 0 |  |  | P-05 | 3D print or foam blister (EST) | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-19 | Pusher spinner 42 mm (EST) | Make | Fabricated part | K4 | Spinner | 1 |  | 0 |  | To source | — | 0 |  |  | — | Not in the BOM: buy or print (—) | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-20 | Gear leg: 6061 1.000 x 0.058 in offcut + printed TPU/PETG foot (EST) | Make | Fabricated part | K5 | Landing_Leg | 4 |  | 0 |  | To make | In-house | 0 |  |  | P-31 | Cut 0.205 m from socket-tube offcut; printed TPU/PETG foot | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
M-21 | Printed PETG gear socket clamp under the boom | Make | Fabricated part | K5 | Gear_Clamp | 4 |  | 0 |  | To make | In-house | 0 |  |  | P-05 | 3D print, PETG | — |  |  |  | cad/params.txt comp= count; cad/mesh/meta.json
N-01 | Carbon lift prop 17 in (design on demand, 2 CW + 2 CCW + 2 spare) | NWA | Lift propulsion | K2 | Lift_Prop | 6 | 0 | 0 |  | Proposed: NWA sponsor offer (verbal) | Nautical Wings Aerospace | 0 |  |  |  | Send spec sheet; designer proposes pitch | — |  |  |  | docs/research/nautical-wings-props.md; sponsorship: team-reported (founders, in person, Oct 2026) | NWA founders offered to sponsor the team (met in person; team-reported, Oct 2026). Sponsorship rules not yet confirmed in writing. Replaces JeeFly 1755 x 6 if confirmed. Fit to X4110S bolt-on adapter (4 mm shaft); hover point 15.2 N per rotor
N-02 | Carbon pusher prop 14 in (design on demand) | NWA | Cruise propulsion | K4 | Pusher_Prop_14in | 2 | 0 | 0 |  | Proposed: NWA sponsor offer (verbal) | Nautical Wings Aerospace | 0 |  |  |  | Send spec sheet; APC 14x8.5EP is the baseline | — |  |  |  | docs/research/nautical-wings-props.md; sponsorship: team-reported (founders, in person, Oct 2026) | NWA founders offered to sponsor the team (met in person; team-reported, Oct 2026). Sponsorship rules not yet confirmed in writing. Replaces APC 14x8.5EP x 3 if confirmed; keep one APC as thrust-stand baseline (team call)
G-01 | Du-Bro Super Lite 3.00 in wheel pair (SKU 300SL, 16.8 g/wheel, 5/32 in axle) | Proposed | Landing gear | K5 | Landing_Leg | 2 | 0 | 0 |  | Proposed: wheeled gear | Gator RC | 6.75 |  |  |  |  | — |  |  |  | inventory/electrical/proposed_lines.json: https://www.gator-rc.com/products/dubro-super-lite-wheels (checked 2026-10-19) | Landing gear on the four existing legs (2 pairs = 4 wheels); raises ground plane 0.048 m EST (wheel radius 0.0381 m + 10 mm axle offset EST), pusher disc clearance 36 to 84 mm. Gator RC page read 2026-10-19: $6.75 per pair, 'Only 1 left' for the product, so one pair must come from another vendor; re-quote before ordering.
G-02 | Du-Bro axle shaft 2-pack, 5/32 in x 2 in (DUB248), with 2 nylon-insert nuts | Proposed | Landing gear | K5 | Landing_Leg | 2 | 0 | 0 |  | Proposed: wheeled gear | Gator RC | 9.05 |  |  |  |  | — |  |  |  | inventory/electrical/proposed_lines.json: https://www.gator-rc.com/products/du-bro-rc-airplane-axle-shafts-2-pack (checked 2026-10-19) | Four axles for four wheels; thread size not published (—), fit-check against leg tip.
G-03 | Du-Bro 5/32 in wheel collars 4-pack (DUB140) | Proposed | Landing gear | K5 | Landing_Leg | 2 | 0 | 0 |  | Proposed: wheeled gear | Gator RC | 2.95 |  |  |  |  | — |  |  |  | inventory/electrical/proposed_lines.json: https://www.gator-rc.com/products/du-bro-wheel-shaft-collars-4-pack (checked 2026-10-19) | Wheel retention; 8 collars, 4 needed, 4 spare.
G-04 | Panasonic 470 uF 35 V low-ESR capacitor | Proposed | Electrical | K2 |  | 6 | 0 | 0 |  | Proposed: electrical | Race Day Quads | 2.49 |  |  |  |  | — |  |  |  | inventory/electrical/proposed_lines.json: https://www.racedayquads.com/products/panasonic-470uf-low-esr-capacitor (checked 2026-10-19) | FC battery-side cap (vendor guide) plus one per lift ESC and pusher ESC; stock, size, lead length not on page (—). Voltage 35 V from title only.
Note on A1: Source: DBF-VTOL repo, inventory/inventory.json (from docs/purchasing/C0_BOM.csv, prices checked 2026-10-13, and cad/params.txt), generated 2026-10-19 by inventory/build_inventory.mjs.

## Lists
Status | Kit | Kit name | Inspected | Type
To order | K1 | Wing | Y | Buy
Ordered | K2 | Booms & lift | N | Make
Received | K3 | Tail | Partial | NWA
Inspected OK | K4 | Pod, avionics & pusher
Rejected | K5 | Landing gear
To make | K6 | Ground support & test
In progress | K7 | Raw stock & consumables
Made
To source
Hold: NWA swap pending
Proposed: confirm with NWA
Cancelled

## Data Sources
Written to | Source | Object | Obtained via | Run at
Inventory!A1:W68 | DBF-VTOL repo | inventory/inventory.json (C0_BOM.csv + cad/params.txt) | Generated by inventory/build_inventory.mjs, run by Claude | 2026-10-19